## Slide 1
PMS
PMS Dashboard
Management review and release recommendation
35%
Derived planning progress
24
Canonical work packages
2
High risk
3
Blocked
Hold the release gate until material blockers and high-risk packages have accountable mitigations.
Project window: 05 Jan 2026 — 18 Dec 2026 | Generated 25 Jul 2026

## Slide 2
HOW TO READ THIS REPORT
Read counts once, then follow relationships
Orbit Project Manager
2
Canonical package
Every Milestone-Specific Work Item plus every Shared Capability, counted once globally.
Primary workstream
The single accountable technical workstream for a package.
Supporting workstream
A contributing workstream; shown as a relationship, never added to the global package total.
Derived planning progress
A simple average of package planning progress; it is not earned value.
Owner labels
Missing ownership is shown explicitly as “Owner Not Assigned”.
Coverage
13 Work Items and 11 canonical Shared Capabilities are included.

## Slide 3
BUSINESS MILESTONE ROADMAP
PMS-01 · Core PMS Scoring Engine
Orbit Project Manager
3
100%
Progress
Low
Risk
Production
Current stage
1
Specific work
4
Shared dependencies
Provide a trusted and repeatable calculation foundation for employee and team performance.
Specific Work Item | Primary | Supporting | Stage | Progress | Owner | Due
WI-01 Validate weighted scoring and result persistence | Database | Backend | Production | 100% | Owner Not Assigned | 18 Sept 2026
Canonical dependencies (references only): SC-AUDIT Audit & Historical Records · SC-DB-VERSION Database Versioning & Migration Integrity · SC-PERIOD Period & Configuration Resolution · SC-VERIFY Release Verification Suite

## Slide 4
BUSINESS MILESTONE ROADMAP
PMS-02 · Team Onboarding & KPI Configuration
Orbit Project Manager
4
72%
Progress
Medium
Risk
Technical Verification
Current stage
1
Specific work
2
Shared dependencies
Allow management to configure teams, periods, KPIs, targets, and weights safely.
Specific Work Item | Primary | Supporting | Stage | Progress | Owner | Due
WI-02 Deliver team and KPI configuration workflow | Frontend | Backend, Database | Technical Verification | 72% | Owner Not Assigned | 18 Sept 2026
Canonical dependencies (references only): SC-UI Common UI States & Responsive Design · SC-DB-VERSION Database Versioning & Migration Integrity

## Slide 5
BUSINESS MILESTONE ROADMAP
PMS-03 · Upload & Data Operations
Orbit Project Manager
5
66%
Progress
High
Risk
Technical Verification
Current stage
1
Specific work
4
Shared dependencies
Provide safe, repeatable ingestion and correction of performance source data.
Specific Work Item | Primary | Supporting | Stage | Progress | Owner | Due
WI-03 Implement atomic upload preview and processing | Backend | Frontend, Database | Technical Verification | 66% | Owner Not Assigned | 18 Sept 2026
Canonical dependencies (references only): SC-AUDIT Audit & Historical Records · SC-DB-VERSION Database Versioning & Migration Integrity · SC-VERIFY Release Verification Suite · SC-SECURITY Security & Environment Controls

## Slide 6
BUSINESS MILESTONE ROADMAP
PMS-04 · Employee Performance Workspace
Orbit Project Manager
6
58%
Progress
Medium
Risk
In Development
Current stage
1
Specific work
5
Shared dependencies
Give employees and managers a focused view of individual performance.
Specific Work Item | Primary | Supporting | Stage | Progress | Owner | Due
WI-04 Build responsive employee result workspace | Frontend | Backend | In Development | 58% | Owner Not Assigned | 18 Sept 2026
Canonical dependencies (references only): SC-AUTH Authentication & Session Security · SC-UI Common UI States & Responsive Design · SC-FE-RELEASE Frontend Release Packaging · SC-RBAC RBAC & Scope Enforcement · SC-VERIFY Release Verification Suite

## Slide 7
BUSINESS MILESTONE ROADMAP
PMS-05 · Team Performance Dashboard
Orbit Project Manager
7
52%
Progress
Medium
Risk
In Development
Current stage
1
Specific work
5
Shared dependencies
Help managers compare team performance and identify attention areas.
Specific Work Item | Primary | Supporting | Stage | Progress | Owner | Due
WI-05 Reconcile team dashboard metrics and drill-down | Frontend | Backend | In Development | 52% | Owner Not Assigned | 18 Sept 2026
Canonical dependencies (references only): SC-UI Common UI States & Responsive Design · SC-FE-RELEASE Frontend Release Packaging · SC-PERIOD Period & Configuration Resolution · SC-RBAC RBAC & Scope Enforcement · SC-VERIFY Release Verification Suite

## Slide 8
BUSINESS MILESTONE ROADMAP
PMS-06 · Management Overview & Strategic Performance
Orbit Project Manager
8
46%
Progress
Medium
Risk
In Development
Current stage
1
Specific work
7
Shared dependencies
Present concise organization-wide performance signals to senior management.
Specific Work Item | Primary | Supporting | Stage | Progress | Owner | Due
WI-06 Assemble executive performance overview | Frontend | Backend, Database | In Development | 46% | Owner Not Assigned | 18 Sept 2026
Canonical dependencies (references only): SC-UI Common UI States & Responsive Design · SC-FE-RELEASE Frontend Release Packaging · SC-MONITOR Monitoring, Backup & Recovery · SC-PERIOD Period & Configuration Resolution · SC-RBAC RBAC & Scope Enforcement · SC-VERIFY Release Verification Suite · SC-EXPORT Shared Export Framework

## Slide 9
BUSINESS MILESTONE ROADMAP
PMS-07 · Trend Analytics & Period Comparisons
Orbit Project Manager
9
41%
Progress
High
Risk
In Development
Current stage
1
Specific work
3
Shared dependencies
Make performance movement across valid reporting periods explainable.
Specific Work Item | Primary | Supporting | Stage | Progress | Owner | Due
WI-07 Resolve comparable periods and trend series | Backend | Frontend, Database | In Development | 41% | Owner Not Assigned | 18 Sept 2026
Canonical dependencies (references only): SC-UI Common UI States & Responsive Design · SC-PERIOD Period & Configuration Resolution · SC-VERIFY Release Verification Suite

## Slide 10
BUSINESS MILESTONE ROADMAP
PMS-08 · Insights, Classification & Planning
Orbit Project Manager
10
20%
Progress
Medium
Risk
Not Started
Current stage
1
Specific work
3
Shared dependencies
Translate results into consistent classifications and practical planning prompts.
Specific Work Item | Primary | Supporting | Stage | Progress | Owner | Due
WI-08 Implement explainable classification rules | Backend | Frontend | Not Started | 20% | Owner Not Assigned | 18 Sept 2026
Canonical dependencies (references only): SC-UI Common UI States & Responsive Design · SC-PERIOD Period & Configuration Resolution · SC-VERIFY Release Verification Suite

## Slide 11
BUSINESS MILESTONE ROADMAP
PMS-09 · Corrective Actions & Follow-up
Orbit Project Manager
11
12%
Progress
Medium
Risk
Not Started
Current stage
1
Specific work
4
Shared dependencies
Track accountable corrective actions from performance findings through closure.
Specific Work Item | Primary | Supporting | Stage | Progress | Owner | Due
WI-09 Deliver corrective action lifecycle | Backend | Frontend, Database | Not Started | 12% | Owner Not Assigned | 18 Sept 2026
Canonical dependencies (references only): SC-AUDIT Audit & Historical Records · SC-UI Common UI States & Responsive Design · SC-RBAC RBAC & Scope Enforcement · SC-VERIFY Release Verification Suite

## Slide 12
BUSINESS MILESTONE ROADMAP
PMS-10 · Reporting, Export & Report Builder
Orbit Project Manager
12
16%
Progress
Medium
Risk
Not Started
Current stage
1
Specific work
6
Shared dependencies
Deliver governed management reports and reusable review exports.
Specific Work Item | Primary | Supporting | Stage | Progress | Owner | Due
WI-10 Build governed report generation foundation | Backend | Frontend, Database | Not Started | 16% | Owner Not Assigned | 18 Sept 2026
Canonical dependencies (references only): SC-UI Common UI States & Responsive Design · SC-FE-RELEASE Frontend Release Packaging · SC-PERIOD Period & Configuration Resolution · SC-RBAC RBAC & Scope Enforcement · SC-VERIFY Release Verification Suite · SC-EXPORT Shared Export Framework

## Slide 13
BUSINESS MILESTONE ROADMAP
PMS-11 · Admin, Users & Access Control
Orbit Project Manager
13
64%
Progress
High
Risk
Technical Verification
Current stage
1
Specific work
7
Shared dependencies
Give administrators safe control over users, roles, and configuration access.
Specific Work Item | Primary | Supporting | Stage | Progress | Owner | Due
WI-11 Verify user and configuration authorization | Backend | Frontend, Database | Technical Verification | 64% | Owner Not Assigned | 18 Sept 2026
Canonical dependencies (references only): SC-AUDIT Audit & Historical Records · SC-AUTH Authentication & Session Security · SC-UI Common UI States & Responsive Design · SC-DB-VERSION Database Versioning & Migration Integrity · SC-RBAC RBAC & Scope Enforcement · SC-VERIFY Release Verification Suite · SC-SECURITY Security & Environment Controls

## Slide 14
BUSINESS MILESTONE ROADMAP
PMS-12 · Testing, Security, Pilot & Production Release
Orbit Project Manager
14
18%
Progress
High
Risk
Not Started
Current stage
1
Specific work
7
Shared dependencies
Establish evidence that Release 1 is secure, supportable, and ready for controlled adoption.
Specific Work Item | Primary | Supporting | Stage | Progress | Owner | Due
WI-12 Establish release verification and pilot gates | Backend | Frontend, Database | Not Started | 18% | Owner Not Assigned | 18 Sept 2026
Canonical dependencies (references only): SC-AUDIT Audit & Historical Records · SC-AUTH Authentication & Session Security · SC-DB-VERSION Database Versioning & Migration Integrity · SC-FE-RELEASE Frontend Release Packaging · SC-MONITOR Monitoring, Backup & Recovery · SC-VERIFY Release Verification Suite · SC-SECURITY Security & Environment Controls

## Slide 15
BUSINESS MILESTONE ROADMAP
PMS-13 · AI Insights & Recommendations
Orbit Project Manager
15
0%
Progress
Medium
Risk
Not Started
Current stage
1
Specific work
1
Shared dependencies
Explore governed AI-assisted insight and recommendation generation after Release 1.
Specific Work Item | Primary | Supporting | Stage | Progress | Owner | Due
WI-13 Define governed AI recommendation evaluation | Backend | Frontend, Database | Not Started | 0% | Owner Not Assigned | 18 Sept 2026
Canonical dependencies (references only): SC-MONITOR Monitoring, Backup & Recovery

## Slide 16
TECHNICAL WORKSTREAM BREAKDOWN
Frontend ownership (1/3)
Orbit Project Manager
16
18
Unique related
6
Primary
12
Supporting
35%
Average progress
Package | Type | Relationship | Stage | Progress | Milestones | Owner
WI-02 Deliver team and KPI configuration workflow | Work Item | Primary | Technical Verification | 72% | Team Onboarding & KPI Configuration | Owner Not Assigned
WI-03 Implement atomic upload preview and processing | Work Item | Supporting | Technical Verification | 66% | Upload & Data Operations | Owner Not Assigned
WI-04 Build responsive employee result workspace | Work Item | Primary | In Development | 58% | Employee Performance Workspace | Owner Not Assigned
WI-05 Reconcile team dashboard metrics and drill-down | Work Item | Primary | In Development | 52% | Team Performance Dashboard | Owner Not Assigned
WI-06 Assemble executive performance overview | Work Item | Primary | In Development | 46% | Management Overview & Strategic Performance | Owner Not Assigned
WI-07 Resolve comparable periods and trend series | Work Item | Supporting | In Development | 41% | Trend Analytics & Period Comparisons | Owner Not Assigned

## Slide 17
TECHNICAL WORKSTREAM BREAKDOWN
Frontend ownership (2/3)
Orbit Project Manager
17
Package | Type | Relationship | Stage | Progress | Milestones | Owner
WI-08 Implement explainable classification rules | Work Item | Supporting | Not Started | 20% | Insights, Classification & Planning | Owner Not Assigned
WI-09 Deliver corrective action lifecycle | Work Item | Supporting | Not Started | 12% | Corrective Actions & Follow-up | Owner Not Assigned
WI-10 Build governed report generation foundation | Work Item | Supporting | Not Started | 16% | Reporting, Export & Report Builder | Owner Not Assigned
WI-11 Verify user and configuration authorization | Work Item | Supporting | Technical Verification | 64% | Admin, Users & Access Control | Owner Not Assigned
WI-12 Establish release verification and pilot gates | Work Item | Supporting | Not Started | 18% | Testing, Security, Pilot & Production Release | Owner Not Assigned
WI-13 Define governed AI recommendation evaluation | Work Item | Supporting | Not Started | 0% | AI Insights & Recommendations | Owner Not Assigned

## Slide 18
TECHNICAL WORKSTREAM BREAKDOWN
Frontend ownership (3/3)
Orbit Project Manager
18
Package | Type | Relationship | Stage | Progress | Milestones | Owner
SC-AUTH Authentication & Session Security | Shared Capability | Supporting | In Development | 55% | Employee Performance Workspace, Admin, Users & Access Control, Testing, Security, Pilot & Production Release | Owner Not Assigned
SC-UI Common UI States & Responsive Design | Shared Capability | Primary | Not Started | 15% | Team Onboarding & KPI Configuration, Employee Performance Workspace, Team Performance Dashboard, Management Overview & Strategic Performance, Trend Analytics & Period Comparisons, Insights, Classification & Planning, Corrective Actions & Follow-up, Reporting, Export & Report Builder, Admin, Users & Access Control | Owner Not Assigned
SC-FE-RELEASE Frontend Release Packaging | Shared Capability | Primary | Not Started | 15% | Employee Performance Workspace, Team Performance Dashboard, Management Overview & Strategic Performance, Reporting, Export & Report Builder, Testing, Security, Pilot & Production Release | Owner Not Assigned
SC-RBAC RBAC & Scope Enforcement | Shared Capability | Supporting | In Development | 50% | Employee Performance Workspace, Team Performance Dashboard, Management Overview & Strategic Performance, Corrective Actions & Follow-up, Reporting, Export & Report Builder, Admin, Users & Access Control | Owner Not Assigned
SC-VERIFY Release Verification Suite | Shared Capability | Supporting | Not Started | 15% | Core PMS Scoring Engine, Upload & Data Operations, Employee Performance Workspace, Team Performance Dashboard, Management Overview & Strategic Performance, Trend Analytics & Period Comparisons, Insights, Classification & Planning, Corrective Actions & Follow-up, Reporting, Export & Report Builder, Admin, Users & Access Control, Testing, Security, Pilot & Production Release | Owner Not Assigned
SC-EXPORT Shared Export Framework | Shared Capability | Supporting | Not Started | 15% | Management Overview & Strategic Performance, Reporting, Export & Report Builder | Owner Not Assigned

## Slide 19
TECHNICAL WORKSTREAM BREAKDOWN
Backend ownership (1/4)
Orbit Project Manager
19
24
Unique related
14
Primary
10
Supporting
35%
Average progress
Package | Type | Relationship | Stage | Progress | Milestones | Owner
WI-01 Validate weighted scoring and result persistence | Work Item | Supporting | Production | 100% | Core PMS Scoring Engine | Owner Not Assigned
WI-02 Deliver team and KPI configuration workflow | Work Item | Supporting | Technical Verification | 72% | Team Onboarding & KPI Configuration | Owner Not Assigned
WI-03 Implement atomic upload preview and processing | Work Item | Primary | Technical Verification | 66% | Upload & Data Operations | Owner Not Assigned
WI-04 Build responsive employee result workspace | Work Item | Supporting | In Development | 58% | Employee Performance Workspace | Owner Not Assigned
WI-05 Reconcile team dashboard metrics and drill-down | Work Item | Supporting | In Development | 52% | Team Performance Dashboard | Owner Not Assigned
WI-06 Assemble executive performance overview | Work Item | Supporting | In Development | 46% | Management Overview & Strategic Performance | Owner Not Assigned

## Slide 20
TECHNICAL WORKSTREAM BREAKDOWN
Backend ownership (2/4)
Orbit Project Manager
20
Package | Type | Relationship | Stage | Progress | Milestones | Owner
WI-07 Resolve comparable periods and trend series | Work Item | Primary | In Development | 41% | Trend Analytics & Period Comparisons | Owner Not Assigned
WI-08 Implement explainable classification rules | Work Item | Primary | Not Started | 20% | Insights, Classification & Planning | Owner Not Assigned
WI-09 Deliver corrective action lifecycle | Work Item | Primary | Not Started | 12% | Corrective Actions & Follow-up | Owner Not Assigned
WI-10 Build governed report generation foundation | Work Item | Primary | Not Started | 16% | Reporting, Export & Report Builder | Owner Not Assigned
WI-11 Verify user and configuration authorization | Work Item | Primary | Technical Verification | 64% | Admin, Users & Access Control | Owner Not Assigned
WI-12 Establish release verification and pilot gates | Work Item | Primary | Not Started | 18% | Testing, Security, Pilot & Production Release | Owner Not Assigned

## Slide 21
TECHNICAL WORKSTREAM BREAKDOWN
Backend ownership (3/4)
Orbit Project Manager
21
Package | Type | Relationship | Stage | Progress | Milestones | Owner
WI-13 Define governed AI recommendation evaluation | Work Item | Primary | Not Started | 0% | AI Insights & Recommendations | Owner Not Assigned
SC-AUDIT Audit & Historical Records | Shared Capability | Supporting | Not Started | 15% | Core PMS Scoring Engine, Upload & Data Operations, Corrective Actions & Follow-up, Admin, Users & Access Control, Testing, Security, Pilot & Production Release | Owner Not Assigned
SC-AUTH Authentication & Session Security | Shared Capability | Primary | In Development | 55% | Employee Performance Workspace, Admin, Users & Access Control, Testing, Security, Pilot & Production Release | Owner Not Assigned
SC-UI Common UI States & Responsive Design | Shared Capability | Supporting | Not Started | 15% | Team Onboarding & KPI Configuration, Employee Performance Workspace, Team Performance Dashboard, Management Overview & Strategic Performance, Trend Analytics & Period Comparisons, Insights, Classification & Planning, Corrective Actions & Follow-up, Reporting, Export & Report Builder, Admin, Users & Access Control | Owner Not Assigned
SC-DB-VERSION Database Versioning & Migration Integrity | Shared Capability | Supporting | Not Started | 15% | Core PMS Scoring Engine, Team Onboarding & KPI Configuration, Upload & Data Operations, Admin, Users & Access Control, Testing, Security, Pilot & Production Release | Owner Not Assigned
SC-FE-RELEASE Frontend Release Packaging | Shared Capability | Supporting | Not Started | 15% | Employee Performance Workspace, Team Performance Dashboard, Management Overview & Strategic Performance, Reporting, Export & Report Builder, Testing, Security, Pilot & Production Release | Owner Not Assigned

## Slide 22
TECHNICAL WORKSTREAM BREAKDOWN
Backend ownership (4/4)
Orbit Project Manager
22
Package | Type | Relationship | Stage | Progress | Milestones | Owner
SC-MONITOR Monitoring, Backup & Recovery | Shared Capability | Supporting | Not Started | 15% | Management Overview & Strategic Performance, Testing, Security, Pilot & Production Release, AI Insights & Recommendations | Owner Not Assigned
SC-PERIOD Period & Configuration Resolution | Shared Capability | Primary | In Development | 45% | Core PMS Scoring Engine, Team Performance Dashboard, Management Overview & Strategic Performance, Trend Analytics & Period Comparisons, Insights, Classification & Planning, Reporting, Export & Report Builder | Owner Not Assigned
SC-RBAC RBAC & Scope Enforcement | Shared Capability | Primary | In Development | 50% | Employee Performance Workspace, Team Performance Dashboard, Management Overview & Strategic Performance, Corrective Actions & Follow-up, Reporting, Export & Report Builder, Admin, Users & Access Control | Owner Not Assigned
SC-VERIFY Release Verification Suite | Shared Capability | Primary | Not Started | 15% | Core PMS Scoring Engine, Upload & Data Operations, Employee Performance Workspace, Team Performance Dashboard, Management Overview & Strategic Performance, Trend Analytics & Period Comparisons, Insights, Classification & Planning, Corrective Actions & Follow-up, Reporting, Export & Report Builder, Admin, Users & Access Control, Testing, Security, Pilot & Production Release | Owner Not Assigned
SC-SECURITY Security & Environment Controls | Shared Capability | Primary | Not Started | 15% | Upload & Data Operations, Admin, Users & Access Control, Testing, Security, Pilot & Production Release | Owner Not Assigned
SC-EXPORT Shared Export Framework | Shared Capability | Primary | Not Started | 15% | Management Overview & Strategic Performance, Reporting, Export & Report Builder | Owner Not Assigned

## Slide 23
TECHNICAL WORKSTREAM BREAKDOWN
Database ownership (1/3)
Orbit Project Manager
23
18
Unique related
4
Primary
14
Supporting
37%
Average progress
Package | Type | Relationship | Stage | Progress | Milestones | Owner
WI-01 Validate weighted scoring and result persistence | Work Item | Primary | Production | 100% | Core PMS Scoring Engine | Owner Not Assigned
WI-02 Deliver team and KPI configuration workflow | Work Item | Supporting | Technical Verification | 72% | Team Onboarding & KPI Configuration | Owner Not Assigned
WI-03 Implement atomic upload preview and processing | Work Item | Supporting | Technical Verification | 66% | Upload & Data Operations | Owner Not Assigned
WI-06 Assemble executive performance overview | Work Item | Supporting | In Development | 46% | Management Overview & Strategic Performance | Owner Not Assigned
WI-07 Resolve comparable periods and trend series | Work Item | Supporting | In Development | 41% | Trend Analytics & Period Comparisons | Owner Not Assigned
WI-09 Deliver corrective action lifecycle | Work Item | Supporting | Not Started | 12% | Corrective Actions & Follow-up | Owner Not Assigned

## Slide 24
TECHNICAL WORKSTREAM BREAKDOWN
Database ownership (2/3)
Orbit Project Manager
24
Package | Type | Relationship | Stage | Progress | Milestones | Owner
WI-10 Build governed report generation foundation | Work Item | Supporting | Not Started | 16% | Reporting, Export & Report Builder | Owner Not Assigned
WI-11 Verify user and configuration authorization | Work Item | Supporting | Technical Verification | 64% | Admin, Users & Access Control | Owner Not Assigned
WI-12 Establish release verification and pilot gates | Work Item | Supporting | Not Started | 18% | Testing, Security, Pilot & Production Release | Owner Not Assigned
WI-13 Define governed AI recommendation evaluation | Work Item | Supporting | Not Started | 0% | AI Insights & Recommendations | Owner Not Assigned
SC-AUDIT Audit & Historical Records | Shared Capability | Primary | Not Started | 15% | Core PMS Scoring Engine, Upload & Data Operations, Corrective Actions & Follow-up, Admin, Users & Access Control, Testing, Security, Pilot & Production Release | Owner Not Assigned
SC-AUTH Authentication & Session Security | Shared Capability | Supporting | In Development | 55% | Employee Performance Workspace, Admin, Users & Access Control, Testing, Security, Pilot & Production Release | Owner Not Assigned

## Slide 25
TECHNICAL WORKSTREAM BREAKDOWN
Database ownership (3/3)
Orbit Project Manager
25
Package | Type | Relationship | Stage | Progress | Milestones | Owner
SC-DB-VERSION Database Versioning & Migration Integrity | Shared Capability | Primary | Not Started | 15% | Core PMS Scoring Engine, Team Onboarding & KPI Configuration, Upload & Data Operations, Admin, Users & Access Control, Testing, Security, Pilot & Production Release | Owner Not Assigned
SC-MONITOR Monitoring, Backup & Recovery | Shared Capability | Primary | Not Started | 15% | Management Overview & Strategic Performance, Testing, Security, Pilot & Production Release, AI Insights & Recommendations | Owner Not Assigned
SC-PERIOD Period & Configuration Resolution | Shared Capability | Supporting | In Development | 45% | Core PMS Scoring Engine, Team Performance Dashboard, Management Overview & Strategic Performance, Trend Analytics & Period Comparisons, Insights, Classification & Planning, Reporting, Export & Report Builder | Owner Not Assigned
SC-RBAC RBAC & Scope Enforcement | Shared Capability | Supporting | In Development | 50% | Employee Performance Workspace, Team Performance Dashboard, Management Overview & Strategic Performance, Corrective Actions & Follow-up, Reporting, Export & Report Builder, Admin, Users & Access Control | Owner Not Assigned
SC-VERIFY Release Verification Suite | Shared Capability | Supporting | Not Started | 15% | Core PMS Scoring Engine, Upload & Data Operations, Employee Performance Workspace, Team Performance Dashboard, Management Overview & Strategic Performance, Trend Analytics & Period Comparisons, Insights, Classification & Planning, Corrective Actions & Follow-up, Reporting, Export & Report Builder, Admin, Users & Access Control, Testing, Security, Pilot & Production Release | Owner Not Assigned
SC-SECURITY Security & Environment Controls | Shared Capability | Supporting | Not Started | 15% | Upload & Data Operations, Admin, Users & Access Control, Testing, Security, Pilot & Production Release | Owner Not Assigned

## Slide 26
DELIVERY PIPELINE
Every canonical package is visible (1/4)
Orbit Project Manager
26
Package | Type | Primary | Supporting | Stage | Progress | Owner | Due
WI-01 Validate weighted scoring and result persistence | Work Item | Database | Backend | Production | 100% | Owner Not Assigned | 18 Sept 2026
WI-02 Deliver team and KPI configuration workflow | Work Item | Frontend | Backend, Database | Technical Verification | 72% | Owner Not Assigned | 18 Sept 2026
WI-03 Implement atomic upload preview and processing | Work Item | Backend | Frontend, Database | Technical Verification | 66% | Owner Not Assigned | 18 Sept 2026
WI-04 Build responsive employee result workspace | Work Item | Frontend | Backend | In Development | 58% | Owner Not Assigned | 18 Sept 2026
WI-05 Reconcile team dashboard metrics and drill-down | Work Item | Frontend | Backend | In Development | 52% | Owner Not Assigned | 18 Sept 2026
WI-06 Assemble executive performance overview | Work Item | Frontend | Backend, Database | In Development | 46% | Owner Not Assigned | 18 Sept 2026

## Slide 27
DELIVERY PIPELINE
Every canonical package is visible (2/4)
Orbit Project Manager
27
Package | Type | Primary | Supporting | Stage | Progress | Owner | Due
WI-07 Resolve comparable periods and trend series | Work Item | Backend | Frontend, Database | In Development | 41% | Owner Not Assigned | 18 Sept 2026
WI-08 Implement explainable classification rules | Work Item | Backend | Frontend | Not Started | 20% | Owner Not Assigned | 18 Sept 2026
WI-09 Deliver corrective action lifecycle | Work Item | Backend | Frontend, Database | Not Started | 12% | Owner Not Assigned | 18 Sept 2026
WI-10 Build governed report generation foundation | Work Item | Backend | Frontend, Database | Not Started | 16% | Owner Not Assigned | 18 Sept 2026
WI-11 Verify user and configuration authorization | Work Item | Backend | Frontend, Database | Technical Verification | 64% | Owner Not Assigned | 18 Sept 2026
WI-12 Establish release verification and pilot gates | Work Item | Backend | Frontend, Database | Not Started | 18% | Owner Not Assigned | 18 Sept 2026

## Slide 28
DELIVERY PIPELINE
Every canonical package is visible (3/4)
Orbit Project Manager
28
Package | Type | Primary | Supporting | Stage | Progress | Owner | Due
WI-13 Define governed AI recommendation evaluation | Work Item | Backend | Frontend, Database | Not Started | 0% | Owner Not Assigned | 18 Sept 2026
SC-AUDIT Audit & Historical Records | Shared Capability | Database | Backend | Not Started | 15% | Owner Not Assigned | 25 Sept 2026
SC-AUTH Authentication & Session Security | Shared Capability | Backend | Frontend, Database | In Development | 55% | Owner Not Assigned | 25 Sept 2026
SC-UI Common UI States & Responsive Design | Shared Capability | Frontend | Backend | Not Started | 15% | Owner Not Assigned | 25 Sept 2026
SC-DB-VERSION Database Versioning & Migration Integrity | Shared Capability | Database | Backend | Not Started | 15% | Owner Not Assigned | 25 Sept 2026
SC-FE-RELEASE Frontend Release Packaging | Shared Capability | Frontend | Backend | Not Started | 15% | Owner Not Assigned | 25 Sept 2026

## Slide 29
DELIVERY PIPELINE
Every canonical package is visible (4/4)
Orbit Project Manager
29
Package | Type | Primary | Supporting | Stage | Progress | Owner | Due
SC-MONITOR Monitoring, Backup & Recovery | Shared Capability | Database | Backend | Not Started | 15% | Owner Not Assigned | 25 Sept 2026
SC-PERIOD Period & Configuration Resolution | Shared Capability | Backend | Database | In Development | 45% | Owner Not Assigned | 25 Sept 2026
SC-RBAC RBAC & Scope Enforcement | Shared Capability | Backend | Frontend, Database | In Development | 50% | Owner Not Assigned | 25 Sept 2026
SC-VERIFY Release Verification Suite | Shared Capability | Backend | Frontend, Database | Not Started | 15% | Owner Not Assigned | 25 Sept 2026
SC-SECURITY Security & Environment Controls | Shared Capability | Backend | Database | Not Started | 15% | Owner Not Assigned | 25 Sept 2026
SC-EXPORT Shared Export Framework | Shared Capability | Backend | Frontend | Not Started | 15% | Owner Not Assigned | 25 Sept 2026

## Slide 30
DELIVERY PIPELINE
The portfolio’s delivery-stage distribution
Orbit Project Manager
30
13
Not Started
7
In Development
3
Technical Verification
0
Business UAT
0
Staging
0
Controlled Pilot
1
Production

## Slide 31
CONTROLLED PILOT
Controlled Pilot scope (1/4)
Orbit Project Manager
31
Pending
Business sign-off
Pending
Technical sign-off
Pending
Final decision
1
Open issues
Scope area | Item | Position / evidence
Pilot team | Inbound | 0 users · Lead: Owner Not Assigned
Pilot team | Outbound | 0 users · Lead: Owner Not Assigned
Pilot team | Pre-Approvals IP Offshore | 0 users · Lead: Owner Not Assigned
Included in Pilot | Audit & Historical Records | Pilot changes must remain traceable.
Included in Pilot | Authentication & Session Security | Required for secure Pilot access.
Included in Pilot | Common UI States & Responsive Design | Responsive and common states are in Pilot scope.

## Slide 32
CONTROLLED PILOT
Controlled Pilot scope (2/4)
Orbit Project Manager
32
Scope area | Item | Position / evidence
Included in Pilot | Database Versioning & Migration Integrity | Migration integrity is required for Pilot.
Included in Pilot | Frontend Release Packaging | Required to package and deploy the Pilot frontend.
Included in Pilot | Period & Configuration Resolution | Included for representative period resolution.
Included in Pilot | RBAC & Scope Enforcement | Required for project and role scope enforcement.
Included in Pilot | Release Verification Suite | Release verification drives Pilot gates.
Included in Pilot | Security & Environment Controls | Environment and security controls are mandatory.

## Slide 33
CONTROLLED PILOT
Controlled Pilot scope (3/4)
Orbit Project Manager
33
Scope area | Item | Position / evidence
Deferred after Pilot | Monitoring, Backup & Recovery | Full operational monitoring automation follows Pilot.
Deferred after Pilot | Shared Export Framework | Advanced export composition follows Pilot.
Entry criterion | Support and rollback owners confirmed | Not Started · Required
Entry criterion | Release and rollback rehearsal passed | Not Started · Required
Entry criterion | Pilot teams, users, and capability scope approved | Not Started · Required
Exit criterion | No open blocking Pilot issues | Not Started · Required

## Slide 34
CONTROLLED PILOT
Controlled Pilot scope (4/4)
Orbit Project Manager
34
Scope area | Item | Position / evidence
Exit criterion | Business and technical evidence assembled | Not Started · Required
Exit criterion | Pilot UAT outcomes accepted | Not Started · Required

## Slide 35
RISKS AND BLOCKERS
Material risks and blockers
Orbit Project Manager
35
Risk | Context | Severity | Status | Owner | Mitigation | Due
Pilot rollback ownership is not signed off | Testing, Security, Pilot & Production Release · Release Verification Suite | Critical | Mitigating | Owner Not Assigned | Assign named operational owners and rehearse rollback before the Pilot gate. | 04 Sept 2026
Legacy upload evidence is incomplete | Upload & Data Operations · Implement atomic upload preview and processing | High | Mitigating | Owner Not Assigned | Complete the pilot data inventory and run atomic rollback verification against every agreed file class. | 14 Aug 2026
Comparable period rules need management confirmation | Trend Analytics & Period Comparisons · Period & Configuration Resolution | High | Open | Owner Not Assigned | Approve explicit comparison rules and preserve them with each report snapshot. | 21 Aug 2026

## Slide 36
MANAGEMENT DECISIONS
Management decisions
Orbit Project Manager
36
Decision | Milestone | Workstreams | Required by | Owner | Status | Recommended direction
Keep AI recommendations outside Release 1 | AI Insights & Recommendations | Frontend, Backend | 31 Jul 2026 | Owner Not Assigned | Approved | Retain AI Insights & Recommendations in Phase 2.
Confirm KPI weight and period validation policy | Team Onboarding & KPI Configuration | Frontend, Backend, Database | 07 Aug 2026 | Owner Not Assigned | Pending | Require a 100 percent active weight total and reject overlapping active periods.
Approve the representative Controlled Pilot dataset | Testing, Security, Pilot & Production Release | Backend, Database | 28 Aug 2026 | Owner Not Assigned | Pending | Use two complete teams plus malformed, duplicate and retry file scenarios.

## Slide 37
UPCOMING DELIVERY
Upcoming delivery commitments (1/2)
Orbit Project Manager
37
Due | Package | Type | Stage | Progress | Primary | Owner | Risk
18 Sept 2026 | WI-02 Deliver team and KPI configuration workflow | Work Item | Technical Verification | 72% | Frontend | Owner Not Assigned | Medium
18 Sept 2026 | WI-03 Implement atomic upload preview and processing | Work Item | Technical Verification | 66% | Backend | Owner Not Assigned | Medium
18 Sept 2026 | WI-04 Build responsive employee result workspace | Work Item | In Development | 58% | Frontend | Owner Not Assigned | Medium
18 Sept 2026 | WI-05 Reconcile team dashboard metrics and drill-down | Work Item | In Development | 52% | Frontend | Owner Not Assigned | Medium
18 Sept 2026 | WI-06 Assemble executive performance overview | Work Item | In Development | 46% | Frontend | Owner Not Assigned | Medium
18 Sept 2026 | WI-07 Resolve comparable periods and trend series | Work Item | In Development | 41% | Backend | Owner Not Assigned | Medium

## Slide 38
UPCOMING DELIVERY
Upcoming delivery commitments (2/2)
Orbit Project Manager
38
Due | Package | Type | Stage | Progress | Primary | Owner | Risk
18 Sept 2026 | WI-08 Implement explainable classification rules | Work Item | Not Started | 20% | Backend | Owner Not Assigned | Medium
18 Sept 2026 | WI-09 Deliver corrective action lifecycle | Work Item | Not Started | 12% | Backend | Owner Not Assigned | Medium
18 Sept 2026 | WI-10 Build governed report generation foundation | Work Item | Not Started | 16% | Backend | Owner Not Assigned | Medium
18 Sept 2026 | WI-11 Verify user and configuration authorization | Work Item | Technical Verification | 64% | Backend | Owner Not Assigned | Medium
18 Sept 2026 | WI-12 Establish release verification and pilot gates | Work Item | Not Started | 18% | Backend | Owner Not Assigned | Medium
18 Sept 2026 | WI-13 Define governed AI recommendation evaluation | Work Item | Not Started | 0% | Backend | Owner Not Assigned | Medium

## Slide 39
FINAL RELEASE RECOMMENDATION
Hold the release gate until material blockers and high-risk packages have accountable mitigations.
3 blocked canonical package(s)
2 high/critical-risk canonical package(s)
1 package(s) in Production
Pilot decision: Pending
Decision owners should confirm the stated release conditions against the latest snapshot before authorizing the next gate.