## Executive Summary
PMS Dashboard — Executive Summary
Snapshot generated 25/07/2026, 16:07:54 UTC · Derived planning progress is not earned value.
Project status | Active |  | Derived planning progress | 35%
Business Milestones | 13 |  | Canonical work packages | 24
Milestone-Specific Work Items | 13 |  | Canonical Shared Capabilities | 11
High-risk packages | 2 |  | Blocked packages | 3
Release 1 progress | 47% |  | Production packages | 1
Delivery-stage distribution
Stage | Not Started | In Development | Technical Verification | Business UAT | Staging | Controlled Pilot | Production
Canonical packages | 13 | 7 | 3 | 0 | 0 | 0 | 1
Final release recommendation
Hold the release gate until material blockers and high-risk packages have accountable mitigations.
Project window
Start date | 2026-01-05 | Target date | 2026-12-18 | Project code | PMS | Snapshot schema | 1

## Milestone Review
Milestone Review
Milestone summaries followed by every Milestone-Specific Work Item. Canonical Shared Capabilities appear once in the final section.
Row Type | Business Milestone | Release | Package Code | Package Name | Package Type | Primary Workstream | Supporting Workstreams | Status | Progress | Delivery Stage | Risk | Owner | Start Date | Due Date | Next Gate | Blocker | Purpose / Description | Shared Dependency References
Milestone Summary | Core PMS Scoring Engine | Release 1 | PMS-01 | Core PMS Scoring Engine | Business Milestone | — | — | Completed | 100% | Production | Low | — | 2026-01-05 | 2026-02-13 | Monitor scoring accuracy in representative datasets. | No blocker recorded | Provide a trusted and repeatable calculation foundation for employee and team performance. | SC-AUDIT Audit & Historical Records; SC-DB-VERSION Database Versioning & Migration Integrity; SC-PERIOD Period & Configuration Resolution; SC-VERIFY Release Verification Suite
Milestone-Specific Work | Core PMS Scoring Engine | Release 1 | WI-01 | Validate weighted scoring and result persistence | Work Item | Database | Backend | Completed | 100% | Production | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-18 | Operational review | No blocker recorded | Validate weighted scoring and result persistence for the PMS-01 Business Milestone. | —
Milestone Summary | Team Onboarding & KPI Configuration | Release 1 | PMS-02 | Team Onboarding & KPI Configuration | Business Milestone | — | — | In Progress | 72% | Technical Verification | Medium | — | 2026-01-19 | 2026-03-20 | Confirm allowed KPI weight and period combinations. | Final validation rules require management confirmation. | Allow management to configure teams, periods, KPIs, targets, and weights safely. | SC-UI Common UI States & Responsive Design; SC-DB-VERSION Database Versioning & Migration Integrity
Milestone-Specific Work | Team Onboarding & KPI Configuration | Release 1 | WI-02 | Deliver team and KPI configuration workflow | Work Item | Frontend | Backend, Database | In Progress | 72% | Technical Verification | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-18 | Phase acceptance review | No blocker recorded | Deliver team and KPI configuration workflow for the PMS-02 Business Milestone. | —
Milestone Summary | Upload & Data Operations | Release 1 | PMS-03 | Upload & Data Operations | Business Milestone | — | — | In Progress | 66% | Technical Verification | High | — | 2026-02-02 | 2026-04-03 | Validate rollback against the agreed pilot dataset. | Representative legacy files are incomplete. | Provide safe, repeatable ingestion and correction of performance source data. | SC-AUDIT Audit & Historical Records; SC-DB-VERSION Database Versioning & Migration Integrity; SC-VERIFY Release Verification Suite; SC-SECURITY Security & Environment Controls
Milestone-Specific Work | Upload & Data Operations | Release 1 | WI-03 | Implement atomic upload preview and processing | Work Item | Backend | Frontend, Database | At Risk | 66% | Technical Verification | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-18 | Phase acceptance review | Representative source evidence requires confirmation. | Implement atomic upload preview and processing for the PMS-03 Business Milestone. | —
Milestone Summary | Employee Performance Workspace | Release 1 | PMS-04 | Employee Performance Workspace | Business Milestone | — | — | In Progress | 58% | In Development | Medium | — | 2026-02-16 | 2026-04-24 | Complete responsive result-detail review. | No blocker recorded | Give employees and managers a focused view of individual performance. | SC-AUTH Authentication & Session Security; SC-UI Common UI States & Responsive Design; SC-FE-RELEASE Frontend Release Packaging; SC-RBAC RBAC & Scope Enforcement; SC-VERIFY Release Verification Suite
Milestone-Specific Work | Employee Performance Workspace | Release 1 | WI-04 | Build responsive employee result workspace | Work Item | Frontend | Backend | In Progress | 58% | In Development | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-18 | Phase acceptance review | No blocker recorded | Build responsive employee result workspace for the PMS-04 Business Milestone. | —
Milestone Summary | Team Performance Dashboard | Release 1 | PMS-05 | Team Performance Dashboard | Business Milestone | — | — | In Progress | 52% | In Development | Medium | — | 2026-03-02 | 2026-05-08 | Reconcile team totals with scoring-engine fixtures. | No blocker recorded | Help managers compare team performance and identify attention areas. | SC-UI Common UI States & Responsive Design; SC-FE-RELEASE Frontend Release Packaging; SC-PERIOD Period & Configuration Resolution; SC-RBAC RBAC & Scope Enforcement; SC-VERIFY Release Verification Suite
Milestone-Specific Work | Team Performance Dashboard | Release 1 | WI-05 | Reconcile team dashboard metrics and drill-down | Work Item | Frontend | Backend | In Progress | 52% | In Development | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-18 | Phase acceptance review | No blocker recorded | Reconcile team dashboard metrics and drill-down for the PMS-05 Business Milestone. | —
Milestone Summary | Management Overview & Strategic Performance | Release 1 | PMS-06 | Management Overview & Strategic Performance | Business Milestone | — | — | In Progress | 46% | In Development | Medium | — | 2026-03-16 | 2026-05-29 | Approve the executive metric hierarchy. | Management metric priority order is awaiting sign-off. | Present concise organization-wide performance signals to senior management. | SC-UI Common UI States & Responsive Design; SC-FE-RELEASE Frontend Release Packaging; SC-MONITOR Monitoring, Backup & Recovery; SC-PERIOD Period & Configuration Resolution; SC-RBAC RBAC & Scope Enforcement; SC-VERIFY Release Verification Suite; SC-EXPORT Shared Export Framework
Milestone-Specific Work | Management Overview & Strategic Performance | Release 1 | WI-06 | Assemble executive performance overview | Work Item | Frontend | Backend, Database | In Progress | 46% | In Development | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-18 | Phase acceptance review | No blocker recorded | Assemble executive performance overview for the PMS-06 Business Milestone. | —
Milestone Summary | Trend Analytics & Period Comparisons | Release 1 | PMS-07 | Trend Analytics & Period Comparisons | Business Milestone | — | — | In Progress | 41% | In Development | High | — | 2026-03-30 | 2026-06-12 | Agree minimum comparable-period eligibility. | Historical period completeness varies by team. | Make performance movement across valid reporting periods explainable. | SC-UI Common UI States & Responsive Design; SC-PERIOD Period & Configuration Resolution; SC-VERIFY Release Verification Suite
Milestone-Specific Work | Trend Analytics & Period Comparisons | Release 1 | WI-07 | Resolve comparable periods and trend series | Work Item | Backend | Frontend, Database | At Risk | 41% | In Development | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-18 | Phase acceptance review | Representative source evidence requires confirmation. | Resolve comparable periods and trend series for the PMS-07 Business Milestone. | —
Milestone Summary | Insights, Classification & Planning | Release 1 | PMS-08 | Insights, Classification & Planning | Business Milestone | — | — | Not Started | 20% | Not Started | Medium | — | 2026-04-20 | 2026-07-03 | Review classification thresholds with management. | No blocker recorded | Translate results into consistent classifications and practical planning prompts. | SC-UI Common UI States & Responsive Design; SC-PERIOD Period & Configuration Resolution; SC-VERIFY Release Verification Suite
Milestone-Specific Work | Insights, Classification & Planning | Release 1 | WI-08 | Implement explainable classification rules | Work Item | Backend | Frontend | Not Started | 20% | Not Started | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-18 | Phase acceptance review | No blocker recorded | Implement explainable classification rules for the PMS-08 Business Milestone. | —
Milestone Summary | Corrective Actions & Follow-up | Release 1 | PMS-09 | Corrective Actions & Follow-up | Business Milestone | — | — | Not Started | 12% | Not Started | Medium | — | 2026-05-04 | 2026-07-24 | Confirm closure evidence and escalation policy. | No blocker recorded | Track accountable corrective actions from performance findings through closure. | SC-AUDIT Audit & Historical Records; SC-UI Common UI States & Responsive Design; SC-RBAC RBAC & Scope Enforcement; SC-VERIFY Release Verification Suite
Milestone-Specific Work | Corrective Actions & Follow-up | Release 1 | WI-09 | Deliver corrective action lifecycle | Work Item | Backend | Frontend, Database | Not Started | 12% | Not Started | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-18 | Phase acceptance review | No blocker recorded | Deliver corrective action lifecycle for the PMS-09 Business Milestone. | —
Milestone Summary | Reporting, Export & Report Builder | Release 1 | PMS-10 | Reporting, Export & Report Builder | Business Milestone | — | — | Not Started | 16% | Not Started | Medium | — | 2026-05-18 | 2026-08-14 | Approve management export templates. | No blocker recorded | Deliver governed management reports and reusable review exports. | SC-UI Common UI States & Responsive Design; SC-FE-RELEASE Frontend Release Packaging; SC-PERIOD Period & Configuration Resolution; SC-RBAC RBAC & Scope Enforcement; SC-VERIFY Release Verification Suite; SC-EXPORT Shared Export Framework
Milestone-Specific Work | Reporting, Export & Report Builder | Release 1 | WI-10 | Build governed report generation foundation | Work Item | Backend | Frontend, Database | Not Started | 16% | Not Started | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-18 | Phase acceptance review | No blocker recorded | Build governed report generation foundation for the PMS-10 Business Milestone. | —
Milestone Summary | Admin, Users & Access Control | Release 1 | PMS-11 | Admin, Users & Access Control | Business Milestone | — | — | In Progress | 64% | Technical Verification | High | — | 2026-02-02 | 2026-06-26 | Complete negative access-path verification. | No blocker recorded | Give administrators safe control over users, roles, and configuration access. | SC-AUDIT Audit & Historical Records; SC-AUTH Authentication & Session Security; SC-UI Common UI States & Responsive Design; SC-DB-VERSION Database Versioning & Migration Integrity; SC-RBAC RBAC & Scope Enforcement; SC-VERIFY Release Verification Suite; SC-SECURITY Security & Environment Controls
Milestone-Specific Work | Admin, Users & Access Control | Release 1 | WI-11 | Verify user and configuration authorization | Work Item | Backend | Frontend, Database | In Progress | 64% | Technical Verification | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-18 | Phase acceptance review | No blocker recorded | Verify user and configuration authorization for the PMS-11 Business Milestone. | —
Milestone Summary | Testing, Security, Pilot & Production Release | Release 1 | PMS-12 | Testing, Security, Pilot & Production Release | Business Milestone | — | — | Not Started | 18% | Not Started | High | — | 2026-06-01 | 2026-10-02 | Nominate pilot, rollback, and support owners. | Pilot team and production support ownership are unconfirmed. | Establish evidence that Release 1 is secure, supportable, and ready for controlled adoption. | SC-AUDIT Audit & Historical Records; SC-AUTH Authentication & Session Security; SC-DB-VERSION Database Versioning & Migration Integrity; SC-FE-RELEASE Frontend Release Packaging; SC-MONITOR Monitoring, Backup & Recovery; SC-VERIFY Release Verification Suite; SC-SECURITY Security & Environment Controls
Milestone-Specific Work | Testing, Security, Pilot & Production Release | Release 1 | WI-12 | Establish release verification and pilot gates | Work Item | Backend | Frontend, Database | Not Started | 18% | Not Started | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-18 | Phase acceptance review | No blocker recorded | Establish release verification and pilot gates for the PMS-12 Business Milestone. | —
Milestone Summary | AI Insights & Recommendations | Phase 2 | PMS-13 | AI Insights & Recommendations | Business Milestone | — | — | Not Started | 0% | Not Started | Medium | — | 2026-10-05 | 2026-12-18 | Define acceptable AI use cases and evaluation criteria. | No blocker recorded | Explore governed AI-assisted insight and recommendation generation after Release 1. | SC-MONITOR Monitoring, Backup & Recovery
Milestone-Specific Work | AI Insights & Recommendations | Phase 2 | WI-13 | Define governed AI recommendation evaluation | Work Item | Backend | Frontend, Database | Not Started | 0% | Not Started | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-18 | Phase acceptance review | No blocker recorded | Define governed AI recommendation evaluation for the PMS-13 Business Milestone. | —
Canonical Shared Capability | Core PMS Scoring Engine; Upload & Data Operations; Corrective Actions & Follow-up; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | Cross-release | SC-AUDIT | Audit & Historical Records | Shared Capability | Database | Backend | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-25 | Capability verification | No blocker recorded | Audit & Historical Records is maintained once for the project and referenced by every dependent Business Milestone. | Core PMS Scoring Engine; Upload & Data Operations; Corrective Actions & Follow-up; Admin, Users & Access Control; Testing, Security, Pilot & Production Release
Canonical Shared Capability | Employee Performance Workspace; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | Cross-release | SC-AUTH | Authentication & Session Security | Shared Capability | Backend | Frontend, Database | In Progress | 55% | In Development | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-25 | Capability verification | No blocker recorded | Authentication & Session Security is maintained once for the project and referenced by every dependent Business Milestone. | Employee Performance Workspace; Admin, Users & Access Control; Testing, Security, Pilot & Production Release
Canonical Shared Capability | Team Onboarding & KPI Configuration; Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Trend Analytics & Period Comparisons; Insights, Classification & Planning; Corrective Actions & Follow-up; Reporting, Export & Report Builder; Admin, Users & Access Control | Cross-release | SC-UI | Common UI States & Responsive Design | Shared Capability | Frontend | Backend | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-25 | Capability verification | No blocker recorded | Common UI States & Responsive Design is maintained once for the project and referenced by every dependent Business Milestone. | Team Onboarding & KPI Configuration; Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Trend Analytics & Period Comparisons; Insights, Classification & Planning; Corrective Actions & Follow-up; Reporting, Export & Report Builder; Admin, Users & Access Control
Canonical Shared Capability | Core PMS Scoring Engine; Team Onboarding & KPI Configuration; Upload & Data Operations; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | Cross-release | SC-DB-VERSION | Database Versioning & Migration Integrity | Shared Capability | Database | Backend | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-25 | Capability verification | No blocker recorded | Database Versioning & Migration Integrity is maintained once for the project and referenced by every dependent Business Milestone. | Core PMS Scoring Engine; Team Onboarding & KPI Configuration; Upload & Data Operations; Admin, Users & Access Control; Testing, Security, Pilot & Production Release
Canonical Shared Capability | Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Reporting, Export & Report Builder; Testing, Security, Pilot & Production Release | Cross-release | SC-FE-RELEASE | Frontend Release Packaging | Shared Capability | Frontend | Backend | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-25 | Capability verification | No blocker recorded | Frontend Release Packaging is maintained once for the project and referenced by every dependent Business Milestone. | Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Reporting, Export & Report Builder; Testing, Security, Pilot & Production Release
Canonical Shared Capability | Management Overview & Strategic Performance; Testing, Security, Pilot & Production Release; AI Insights & Recommendations | Cross-release | SC-MONITOR | Monitoring, Backup & Recovery | Shared Capability | Database | Backend | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-25 | Capability verification | No blocker recorded | Monitoring, Backup & Recovery is maintained once for the project and referenced by every dependent Business Milestone. | Management Overview & Strategic Performance; Testing, Security, Pilot & Production Release; AI Insights & Recommendations
Canonical Shared Capability | Core PMS Scoring Engine; Team Performance Dashboard; Management Overview & Strategic Performance; Trend Analytics & Period Comparisons; Insights, Classification & Planning; Reporting, Export & Report Builder | Cross-release | SC-PERIOD | Period & Configuration Resolution | Shared Capability | Backend | Database | In Progress | 45% | In Development | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-25 | Capability verification | No blocker recorded | Period & Configuration Resolution is maintained once for the project and referenced by every dependent Business Milestone. | Core PMS Scoring Engine; Team Performance Dashboard; Management Overview & Strategic Performance; Trend Analytics & Period Comparisons; Insights, Classification & Planning; Reporting, Export & Report Builder
Canonical Shared Capability | Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Corrective Actions & Follow-up; Reporting, Export & Report Builder; Admin, Users & Access Control | Cross-release | SC-RBAC | RBAC & Scope Enforcement | Shared Capability | Backend | Frontend, Database | In Progress | 50% | In Development | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-25 | Capability verification | No blocker recorded | RBAC & Scope Enforcement is maintained once for the project and referenced by every dependent Business Milestone. | Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Corrective Actions & Follow-up; Reporting, Export & Report Builder; Admin, Users & Access Control
Canonical Shared Capability | Core PMS Scoring Engine; Upload & Data Operations; Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Trend Analytics & Period Comparisons; Insights, Classification & Planning; Corrective Actions & Follow-up; Reporting, Export & Report Builder; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | Cross-release | SC-VERIFY | Release Verification Suite | Shared Capability | Backend | Frontend, Database | Not Started | 15% | Not Started | High | Owner Not Assigned | 2026-02-02 | 2026-09-25 | Capability verification | Full release evidence depends on completion of milestone workflows. | Release Verification Suite is maintained once for the project and referenced by every dependent Business Milestone. | Core PMS Scoring Engine; Upload & Data Operations; Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Trend Analytics & Period Comparisons; Insights, Classification & Planning; Corrective Actions & Follow-up; Reporting, Export & Report Builder; Admin, Users & Access Control; Testing, Security, Pilot & Production Release
Canonical Shared Capability | Upload & Data Operations; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | Cross-release | SC-SECURITY | Security & Environment Controls | Shared Capability | Backend | Database | Not Started | 15% | Not Started | High | Owner Not Assigned | 2026-02-02 | 2026-09-25 | Capability verification | No blocker recorded | Security & Environment Controls is maintained once for the project and referenced by every dependent Business Milestone. | Upload & Data Operations; Admin, Users & Access Control; Testing, Security, Pilot & Production Release
Canonical Shared Capability | Management Overview & Strategic Performance; Reporting, Export & Report Builder | Cross-release | SC-EXPORT | Shared Export Framework | Shared Capability | Backend | Frontend | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-02-02 | 2026-09-25 | Capability verification | No blocker recorded | Shared Export Framework is maintained once for the project and referenced by every dependent Business Milestone. | Management Overview & Strategic Performance; Reporting, Export & Report Builder

## Workstream Review
Technical Workstream Review
One row per package–workstream relationship. Primary and Supporting assignments remain explicit; global totals use canonical package keys.
Workstream | Relationship | Package Code | Package Name | Package Type | Business Milestones | Status | Progress | Delivery Stage | Risk | Owner | Due Date | Blocker
Frontend | Primary | WI-02 | Deliver team and KPI configuration workflow | Work Item | Team Onboarding & KPI Configuration | In Progress | 72% | Technical Verification | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Frontend | Supporting | WI-03 | Implement atomic upload preview and processing | Work Item | Upload & Data Operations | At Risk | 66% | Technical Verification | Medium | Owner Not Assigned | 2026-09-18 | Representative source evidence requires confirmation.
Frontend | Primary | WI-04 | Build responsive employee result workspace | Work Item | Employee Performance Workspace | In Progress | 58% | In Development | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Frontend | Primary | WI-05 | Reconcile team dashboard metrics and drill-down | Work Item | Team Performance Dashboard | In Progress | 52% | In Development | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Frontend | Primary | WI-06 | Assemble executive performance overview | Work Item | Management Overview & Strategic Performance | In Progress | 46% | In Development | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Frontend | Supporting | WI-07 | Resolve comparable periods and trend series | Work Item | Trend Analytics & Period Comparisons | At Risk | 41% | In Development | Medium | Owner Not Assigned | 2026-09-18 | Representative source evidence requires confirmation.
Frontend | Supporting | WI-08 | Implement explainable classification rules | Work Item | Insights, Classification & Planning | Not Started | 20% | Not Started | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Frontend | Supporting | WI-09 | Deliver corrective action lifecycle | Work Item | Corrective Actions & Follow-up | Not Started | 12% | Not Started | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Frontend | Supporting | WI-10 | Build governed report generation foundation | Work Item | Reporting, Export & Report Builder | Not Started | 16% | Not Started | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Frontend | Supporting | WI-11 | Verify user and configuration authorization | Work Item | Admin, Users & Access Control | In Progress | 64% | Technical Verification | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Frontend | Supporting | WI-12 | Establish release verification and pilot gates | Work Item | Testing, Security, Pilot & Production Release | Not Started | 18% | Not Started | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Frontend | Supporting | WI-13 | Define governed AI recommendation evaluation | Work Item | AI Insights & Recommendations | Not Started | 0% | Not Started | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Frontend | Supporting | SC-AUTH | Authentication & Session Security | Shared Capability | Employee Performance Workspace; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | In Progress | 55% | In Development | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Frontend | Primary | SC-UI | Common UI States & Responsive Design | Shared Capability | Team Onboarding & KPI Configuration; Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Trend Analytics & Period Comparisons; Insights, Classification & Planning; Corrective Actions & Follow-up; Reporting, Export & Report Builder; Admin, Users & Access Control | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Frontend | Primary | SC-FE-RELEASE | Frontend Release Packaging | Shared Capability | Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Reporting, Export & Report Builder; Testing, Security, Pilot & Production Release | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Frontend | Supporting | SC-RBAC | RBAC & Scope Enforcement | Shared Capability | Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Corrective Actions & Follow-up; Reporting, Export & Report Builder; Admin, Users & Access Control | In Progress | 50% | In Development | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Frontend | Supporting | SC-VERIFY | Release Verification Suite | Shared Capability | Core PMS Scoring Engine; Upload & Data Operations; Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Trend Analytics & Period Comparisons; Insights, Classification & Planning; Corrective Actions & Follow-up; Reporting, Export & Report Builder; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | Not Started | 15% | Not Started | High | Owner Not Assigned | 2026-09-25 | Full release evidence depends on completion of milestone workflows.
Frontend | Supporting | SC-EXPORT | Shared Export Framework | Shared Capability | Management Overview & Strategic Performance; Reporting, Export & Report Builder | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Backend | Supporting | WI-01 | Validate weighted scoring and result persistence | Work Item | Core PMS Scoring Engine | Completed | 100% | Production | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Backend | Supporting | WI-02 | Deliver team and KPI configuration workflow | Work Item | Team Onboarding & KPI Configuration | In Progress | 72% | Technical Verification | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Backend | Primary | WI-03 | Implement atomic upload preview and processing | Work Item | Upload & Data Operations | At Risk | 66% | Technical Verification | Medium | Owner Not Assigned | 2026-09-18 | Representative source evidence requires confirmation.
Backend | Supporting | WI-04 | Build responsive employee result workspace | Work Item | Employee Performance Workspace | In Progress | 58% | In Development | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Backend | Supporting | WI-05 | Reconcile team dashboard metrics and drill-down | Work Item | Team Performance Dashboard | In Progress | 52% | In Development | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Backend | Supporting | WI-06 | Assemble executive performance overview | Work Item | Management Overview & Strategic Performance | In Progress | 46% | In Development | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Backend | Primary | WI-07 | Resolve comparable periods and trend series | Work Item | Trend Analytics & Period Comparisons | At Risk | 41% | In Development | Medium | Owner Not Assigned | 2026-09-18 | Representative source evidence requires confirmation.
Backend | Primary | WI-08 | Implement explainable classification rules | Work Item | Insights, Classification & Planning | Not Started | 20% | Not Started | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Backend | Primary | WI-09 | Deliver corrective action lifecycle | Work Item | Corrective Actions & Follow-up | Not Started | 12% | Not Started | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Backend | Primary | WI-10 | Build governed report generation foundation | Work Item | Reporting, Export & Report Builder | Not Started | 16% | Not Started | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Backend | Primary | WI-11 | Verify user and configuration authorization | Work Item | Admin, Users & Access Control | In Progress | 64% | Technical Verification | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Backend | Primary | WI-12 | Establish release verification and pilot gates | Work Item | Testing, Security, Pilot & Production Release | Not Started | 18% | Not Started | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Backend | Primary | WI-13 | Define governed AI recommendation evaluation | Work Item | AI Insights & Recommendations | Not Started | 0% | Not Started | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Backend | Supporting | SC-AUDIT | Audit & Historical Records | Shared Capability | Core PMS Scoring Engine; Upload & Data Operations; Corrective Actions & Follow-up; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Backend | Primary | SC-AUTH | Authentication & Session Security | Shared Capability | Employee Performance Workspace; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | In Progress | 55% | In Development | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Backend | Supporting | SC-UI | Common UI States & Responsive Design | Shared Capability | Team Onboarding & KPI Configuration; Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Trend Analytics & Period Comparisons; Insights, Classification & Planning; Corrective Actions & Follow-up; Reporting, Export & Report Builder; Admin, Users & Access Control | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Backend | Supporting | SC-DB-VERSION | Database Versioning & Migration Integrity | Shared Capability | Core PMS Scoring Engine; Team Onboarding & KPI Configuration; Upload & Data Operations; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Backend | Supporting | SC-FE-RELEASE | Frontend Release Packaging | Shared Capability | Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Reporting, Export & Report Builder; Testing, Security, Pilot & Production Release | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Backend | Supporting | SC-MONITOR | Monitoring, Backup & Recovery | Shared Capability | Management Overview & Strategic Performance; Testing, Security, Pilot & Production Release; AI Insights & Recommendations | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Backend | Primary | SC-PERIOD | Period & Configuration Resolution | Shared Capability | Core PMS Scoring Engine; Team Performance Dashboard; Management Overview & Strategic Performance; Trend Analytics & Period Comparisons; Insights, Classification & Planning; Reporting, Export & Report Builder | In Progress | 45% | In Development | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Backend | Primary | SC-RBAC | RBAC & Scope Enforcement | Shared Capability | Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Corrective Actions & Follow-up; Reporting, Export & Report Builder; Admin, Users & Access Control | In Progress | 50% | In Development | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Backend | Primary | SC-VERIFY | Release Verification Suite | Shared Capability | Core PMS Scoring Engine; Upload & Data Operations; Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Trend Analytics & Period Comparisons; Insights, Classification & Planning; Corrective Actions & Follow-up; Reporting, Export & Report Builder; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | Not Started | 15% | Not Started | High | Owner Not Assigned | 2026-09-25 | Full release evidence depends on completion of milestone workflows.
Backend | Primary | SC-SECURITY | Security & Environment Controls | Shared Capability | Upload & Data Operations; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | Not Started | 15% | Not Started | High | Owner Not Assigned | 2026-09-25 | No blocker recorded
Backend | Primary | SC-EXPORT | Shared Export Framework | Shared Capability | Management Overview & Strategic Performance; Reporting, Export & Report Builder | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Database | Primary | WI-01 | Validate weighted scoring and result persistence | Work Item | Core PMS Scoring Engine | Completed | 100% | Production | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Database | Supporting | WI-02 | Deliver team and KPI configuration workflow | Work Item | Team Onboarding & KPI Configuration | In Progress | 72% | Technical Verification | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Database | Supporting | WI-03 | Implement atomic upload preview and processing | Work Item | Upload & Data Operations | At Risk | 66% | Technical Verification | Medium | Owner Not Assigned | 2026-09-18 | Representative source evidence requires confirmation.
Database | Supporting | WI-06 | Assemble executive performance overview | Work Item | Management Overview & Strategic Performance | In Progress | 46% | In Development | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Database | Supporting | WI-07 | Resolve comparable periods and trend series | Work Item | Trend Analytics & Period Comparisons | At Risk | 41% | In Development | Medium | Owner Not Assigned | 2026-09-18 | Representative source evidence requires confirmation.
Database | Supporting | WI-09 | Deliver corrective action lifecycle | Work Item | Corrective Actions & Follow-up | Not Started | 12% | Not Started | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Database | Supporting | WI-10 | Build governed report generation foundation | Work Item | Reporting, Export & Report Builder | Not Started | 16% | Not Started | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Database | Supporting | WI-11 | Verify user and configuration authorization | Work Item | Admin, Users & Access Control | In Progress | 64% | Technical Verification | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Database | Supporting | WI-12 | Establish release verification and pilot gates | Work Item | Testing, Security, Pilot & Production Release | Not Started | 18% | Not Started | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Database | Supporting | WI-13 | Define governed AI recommendation evaluation | Work Item | AI Insights & Recommendations | Not Started | 0% | Not Started | Medium | Owner Not Assigned | 2026-09-18 | No blocker recorded
Database | Primary | SC-AUDIT | Audit & Historical Records | Shared Capability | Core PMS Scoring Engine; Upload & Data Operations; Corrective Actions & Follow-up; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Database | Supporting | SC-AUTH | Authentication & Session Security | Shared Capability | Employee Performance Workspace; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | In Progress | 55% | In Development | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Database | Primary | SC-DB-VERSION | Database Versioning & Migration Integrity | Shared Capability | Core PMS Scoring Engine; Team Onboarding & KPI Configuration; Upload & Data Operations; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Database | Primary | SC-MONITOR | Monitoring, Backup & Recovery | Shared Capability | Management Overview & Strategic Performance; Testing, Security, Pilot & Production Release; AI Insights & Recommendations | Not Started | 15% | Not Started | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Database | Supporting | SC-PERIOD | Period & Configuration Resolution | Shared Capability | Core PMS Scoring Engine; Team Performance Dashboard; Management Overview & Strategic Performance; Trend Analytics & Period Comparisons; Insights, Classification & Planning; Reporting, Export & Report Builder | In Progress | 45% | In Development | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Database | Supporting | SC-RBAC | RBAC & Scope Enforcement | Shared Capability | Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Corrective Actions & Follow-up; Reporting, Export & Report Builder; Admin, Users & Access Control | In Progress | 50% | In Development | Medium | Owner Not Assigned | 2026-09-25 | No blocker recorded
Database | Supporting | SC-VERIFY | Release Verification Suite | Shared Capability | Core PMS Scoring Engine; Upload & Data Operations; Employee Performance Workspace; Team Performance Dashboard; Management Overview & Strategic Performance; Trend Analytics & Period Comparisons; Insights, Classification & Planning; Corrective Actions & Follow-up; Reporting, Export & Report Builder; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | Not Started | 15% | Not Started | High | Owner Not Assigned | 2026-09-25 | Full release evidence depends on completion of milestone workflows.
Database | Supporting | SC-SECURITY | Security & Environment Controls | Shared Capability | Upload & Data Operations; Admin, Users & Access Control; Testing, Security, Pilot & Production Release | Not Started | 15% | Not Started | High | Owner Not Assigned | 2026-09-25 | No blocker recorded

## Risks & Decisions
Risks & Decisions
Material risk ownership and the decisions management must make.
Risks
Risk | Description | Milestone | Related Package | Primary Workstream | Probability | Impact | Severity | Owner | Mitigation | Due Date | Status | Record ID
Pilot rollback ownership is not signed off | Controlled Pilot entry remains blocked until support and rollback accountability is accepted. | Testing, Security, Pilot & Production Release | Release Verification Suite | Backend | 4 | 5 | Critical | Owner Not Assigned | Assign named operational owners and rehearse rollback before the Pilot gate. | 2026-09-04 | Mitigating | 80000000-0000-4000-8000-000000000003
Legacy upload evidence is incomplete | Representative legacy files do not yet cover every malformed and retry scenario required for release confidence. | Upload & Data Operations | Implement atomic upload preview and processing | Backend | 4 | 4 | High | Owner Not Assigned | Complete the pilot data inventory and run atomic rollback verification against every agreed file class. | 2026-08-14 | Mitigating | 80000000-0000-4000-8000-000000000001
Comparable period rules need management confirmation | Trend results can be misleading until the organization agrees how missing and partial periods are resolved. | Trend Analytics & Period Comparisons | Period & Configuration Resolution | Backend | 3 | 4 | High | Owner Not Assigned | Approve explicit comparison rules and preserve them with each report snapshot. | 2026-08-21 | Open | 80000000-0000-4000-8000-000000000002
Management Decisions
Decision | Description | Milestone | Affected Workstreams | Required By | Recommended Direction | Owner | Status | Decision | Decided At | Record ID
Keep AI recommendations outside Release 1 | Management must preserve the agreed release boundary while evaluation and governance criteria mature. | AI Insights & Recommendations | Frontend, Backend | 2026-07-31 | Retain AI Insights & Recommendations in Phase 2. | Owner Not Assigned | Approved | AI recommendations remain Phase 2 and are excluded from the first production release. | 2026-07-25 08:00 | 81000000-0000-4000-8000-000000000003
Confirm KPI weight and period validation policy | Management must decide which weight totals and period overlaps are acceptable during team configuration. | Team Onboarding & KPI Configuration | Frontend, Backend, Database | 2026-08-07 | Require a 100 percent active weight total and reject overlapping active periods. | Owner Not Assigned | Pending | Decision pending |  | 81000000-0000-4000-8000-000000000001
Approve the representative Controlled Pilot dataset | The release team needs approval for the teams, periods and source-file classes included in Pilot verification. | Testing, Security, Pilot & Production Release | Backend, Database | 2026-08-28 | Use two complete teams plus malformed, duplicate and retry file scenarios. | Owner Not Assigned | Pending | Decision pending |  | 81000000-0000-4000-8000-000000000002

## Pilot Scope Review
Controlled Pilot Scope Review
Pilot teams, capabilities, criteria, limitations, issues and approvals at the snapshot time.
Overview and sign-off
Pilot | PMS Controlled Pilot | Support Owner | Owner Not Assigned | Rollback Owner | Owner Not Assigned | Business Sign-off | Pending
Technical Sign-off | Pending | Final Decision | Pending | Decision | Decision pending | Known Limitations | AI Insights & Recommendations and advanced report composition remain outside the first Pilot scope. Pilot support is limited to agreed operating hours.
Pilot teams and users
Team | Lead | Pilot Users
Inbound | Owner Not Assigned | No users assigned
Outbound | Owner Not Assigned | No users assigned
Pre-Approvals IP Offshore | Owner Not Assigned | No users assigned
Included and deferred capabilities
Disposition | Capability Code | Capability | Notes
Included in Pilot | SC-AUDIT | Audit & Historical Records | Pilot changes must remain traceable.
Included in Pilot | SC-AUTH | Authentication & Session Security | Required for secure Pilot access.
Included in Pilot | SC-UI | Common UI States & Responsive Design | Responsive and common states are in Pilot scope.
Included in Pilot | SC-DB-VERSION | Database Versioning & Migration Integrity | Migration integrity is required for Pilot.
Included in Pilot | SC-FE-RELEASE | Frontend Release Packaging | Required to package and deploy the Pilot frontend.
Included in Pilot | SC-PERIOD | Period & Configuration Resolution | Included for representative period resolution.
Included in Pilot | SC-RBAC | RBAC & Scope Enforcement | Required for project and role scope enforcement.
Included in Pilot | SC-VERIFY | Release Verification Suite | Release verification drives Pilot gates.
Included in Pilot | SC-SECURITY | Security & Environment Controls | Environment and security controls are mandatory.
Deferred after Pilot | SC-MONITOR | Monitoring, Backup & Recovery | Full operational monitoring automation follows Pilot.
Deferred after Pilot | SC-EXPORT | Shared Export Framework | Advanced export composition follows Pilot.
Entry and exit criteria
Gate | Code | Criterion | Required | Status | Evidence
Entry | ENTRY-OWNERS | Support and rollback owners confirmed | Yes | Not Started | Not recorded
Entry | ENTRY-ROLLBACK | Release and rollback rehearsal passed | Yes | Not Started | Not recorded
Entry | ENTRY-SCOPE | Pilot teams, users, and capability scope approved | Yes | Not Started | Not recorded
Exit | EXIT-BLOCKERS | No open blocking Pilot issues | Yes | Not Started | Not recorded
Exit | EXIT-SIGNOFF | Business and technical evidence assembled | Yes | Not Started | Not recorded
Exit | EXIT-UAT | Pilot UAT outcomes accepted | Yes | Not Started | Not recorded
Pilot issue log
Issue | Severity | Status | Blocking | Owner | Due Date | Mitigation
Pilot support roster requires final confirmation | High | Open | Yes | Owner Not Assigned | 2026-08-28 | Confirm primary and backup support contacts before the Entry gate review.

## Final Feedback and Sign-off
Final Feedback and Sign-off
Complete this sheet during the management review. Editable fields are shaded pale blue.
Snapshot reference
Project | PMS Dashboard | Project Code | PMS | Generated | 2026-07-25 16:08 | Canonical Packages | 24
Management feedback
Executive feedback
Conditions before the next gate
Accepted risks
Decisions confirmed
Actions and owners
Final sign-off
Role | Name | Decision | Date | Signature / Reference | Comments
Business Owner |  | Pending
Technical Owner |  | Pending
Project Manager |  | Pending
Reviewer |  | Pending